Fylde Coast Runners

EVENT MANAGEMENT DOCUMENT

WINDMILL 10k Road Race Sunday 12 November 2017

Table of Contents

Event Information	4

Introduction	4

Management & Planning	4

Local Authority Information	4

Policy Statements	4

HEALTH & SAFETY POLICY STATEMENT	4

EQUALITY ACT 2010 POLICY STATEMENT	5

CHILDREN ACT 1989/2004 POLICY STATEMENT	5

Roles & Responsibilities	5

COURSE STEWARDS	5

WATER STATION STEWARDS	5

Event Profile	6

Insurance	7

UK Athletics Race Licence	7

Insurance Information & Policy Coverage	8

Staff & Stewards	9

Event Staff	9

Core Staff	9

Registration	9

Finish	9

Course Stewards	10

Water Station Stewards	10

Course & Venue	11

Venue Location	11

Start Location	11

Finish Location	12

Run Route	12

Surface & Inspections	12

Event Signage	12

Aid Station	13

Car Parking	13

Venue Information	13

Toilet Facilities	13

Risk Assessments	14

General Event Risk Assessment	14

Course Risk Assessment	15

Medical Risk Assessment	16

Weather Risk Assessment	17

Medical Information	19

Determined Medical Coverage	19

Medical Personnel On Site	19

Communications	20

Event Communications Profile	20

Event Radio Network	20

Event Specific Information	21

Cancellation Policy	21

Weather Information	21

Emergency Planning	21

DEFINITION	21

BOMB WARNING RECEIVED	21

COMPLETE EVACUATION OF THE EVENT AREAS	22

SUSPICIOUS PACKAGES	22

FIRE	22

HOSTILE AND NON HOSTILE DEMONSTRATIONS	22

CRIMINAL INCIDENT	22

ROAD INCIDENT	22

EMERGENCY SITUATION	22

Lost Items/Property	23

Lost Children	23

# Event Information

## Introduction

This document provides a summary of information for all aspects of the event, for the benefit of those involved in its organisation and delivery. This includes details of the event itinerary together with event personnel, site plans, routes, planning documents, schedules, risk assessment and cover provided by the medical services, stewards and emergency services.

The event is a foot race consisting of a measured 10-kilometre distance, starting and finishing at Fairhaven Lake, Lytham St Annes.

The event will take place on Sunday 12th November 2017, starting at 11.05am, after a two-minute silence and prayer to mark Remembrance Sunday. The registration area is on the adjacent to the Fairhaven Lake Cafe. This is where all competitors are directed to go before the start. All competitors must collect their race number before competing. Registration opens at 9.00am.

## Management & Planning

A number of key factors have been considered by Fylde Coast Runners before promoting the event. The date has been checked as to not coincide with any similar event on the same day in the area using the events calendars at runbritain.com. The route, which has been used in previous years, was checked for access or any changes on the, walkways or cycle paths within the park. The venue has been booked and checked whether the event can be hosted from there on the day. A preliminary risk assessment of the course has been undertaken to check suitability of the course. Checks have been made as to the availability of stewards and marshals on the day. Seasonal weather conditions have also been considered. After all these aspects have been considered, the event was proven to be acceptable and safe to promote.

## Local Authority Information

A notice of intention has been sent to Fylde Council for consideration and approval from the Safety Advisory Group. The following departments/organisations have been informed about the event for pre-planning purposes:

• Fylde Borough Council forwarded to all relevant departments
  • Blackpool Police (Events)
  • Lancashire Ambulance Service (via SAG)
  • Lancashire Fire & Rescue Service (via SAG)

• Blackpool, Fylde & Wyre Hospitals (via SAG)

## Policy Statements

HEALTH & SAFETY POLICY STATEMENT
It is an important duty of this organisation, in the conduct of its operations, to ensure a safe and healthy working environment for all its staff, stewards and volunteers. The organisation accepts the fact that this implies a corresponding duty of ensuring that necessary organisation, equipment and training is provided to fulfill this obligation. An effective health and safety policy requires the full collaboration and co-operation of all staff, stewards and volunteers; everybody is asked to read this policy and accept their own personal responsibility for health and safety at work.

It is the responsibility of the Event Manager:

a. to maintain the spirit and letter of the principles incorporated in the relevant legislation to ensure the safest systems of work and a safe, healthy working environment.

b. by consultation and joint involvement of management and staff, stewards and volunteers, to enlist the active interest, participation and support of staff, stewards and volunteers in promoting good standards.

It is the responsibility of all officials, stewards and volunteers:

a. to take all reasonable care for the health and safety of him/herself and of fellow staff, stewards and volunteers and to report any hazard which cannot be controlled personally.

b. to co-operate with the organisation by observing safety rules and complying with any measures designed to ensure a safe and healthy working environment.

The role of ‘Event Safety Officer (ESO)’ is of vital importance for maintaining a continuous and critical scrutiny of working conditions throughout the workplace, reviewing safety performance and promoting safer working. The designated ESO is the Event Manager. The Event Manager accepts ultimate responsibility for health and safety within the organisation as a whole. All staff, stewards and volunteers generally are expected to support and implement this policy wholeheartedly.

### EQUALITY ACT 2010 POLICY STATEMENT

As an organisation, Fylde Coast Runners fully complies with the regulations and amendments contained within the Equality Act 2010. Specifically, we recognise the protected characteristics of the following; Age, Disability, Gender Reassignment, Marriage and Civil Partnerships, Pregnancy and Maternity, Race, Religion or Beliefs, Sex and Sexual Orientation.

No aspect of the event compromises any of the Equality Act 2010 characteristics, and as an organisation uphold the values of all of the regulations and amendments. A copy of the Equality Act 2010 has been obtained and is available to view at the events office or public viewing or for reference by event staff.

### CHILDREN ACT 1989/2004 POLICY STATEMENT

As an organisation, Fylde Coast Runners fully complies with the regulations and amendments contained within the Children Act 1989/2004 and have taken the following pre-cautions to ensure a duty of care to minors. Minors under the age of 18 must have their entry form signed and dated by a parent or guardian. The medical services provider, Remote Medical Services, have all their personnel CRB checked. The event technical advisor and event manager are CRB checked.

No aspect of the event compromises any of the Children Act 1989/2004 and as an organisation uphold the values of all of the regulations and amendments. A copy of the Act has been obtained and is available to view at the events office or public viewing or for reference by event staff.

## Roles & Responsibilities

### COURSE STEWARDS

The main responsibilities of the stewards are to act as markers on the course and to provide safety for runners in that area of the course. They will also assist the police and other emergency services should the need arise. Stewards are also required to report any injuries or runners requiring medical assistance.

Whilst on duty, stewards will:

Concentrate only on their duties. Not use mobile phones, iPods or other electronic devices unless required to report an emergency or medical assistance request to the First Aid Point.

Not leave their place without permission unless told to do so by the Event Manager or Police.

Not consume or be under the influence of alcohol or drugs.

Remain calm and be courteous towards members of the public and runners.

Wear distinctive hi-visibility clothing at all times.

Be familiar with the course to direct runners and answer any relevant questions.

Be prepared to assist in other areas of the event if the need arises.

Be responsible and over the age of 18.

Stewards will be required to stand at their designated point for quite some time. We advise that they wear clothing appropriate for the time of year and have a flask of warm drink or drinks bottles. We also advise a trip to the toilet before the start of the race. If a steward wants to leave post at any time during the event, they must call in to the first aid point to have a replacement steward sent to their point. STEWARDS ARE NOT TO LEAVE THEIR POINT UNATTENDED UNDER ANY CIRCUMSTANCES. On the day of the events, all stewards and supervisors will be walked or driven onto the route after being briefed on their specific role.

### WATER STATION STEWARDS

The main responsibilities of the stewards are to distribute bottled water to runners from their designated point. They will also assist the police and other emergency services should the need arise. Water Station Stewards are also required to report any injuries or runners requiring medical assistance.

Stewards will be required to stand at their designated point for quite some time. We advise that they wear clothing appropriate for the time of year and have a flask of warm drink or drinks bottles. We also advise a trip to the toilet before the start of the race. If a steward wants to leave post at any time during the event, they must call in to the first aid point to have a replacement steward sent to their point. STEWARDS ARE NOT TO LEAVE THEIR POINT UNATTENDED UNDER ANY CIRCUMSTANCES.

Water Station Best Practice

Please remove the bottle tops before handing to the runner.

Throw bottle tops in the bags provided.

Place enough opened bottles on the table to help you grab them when it gets busy and the runners approach in groups.

Collect as many discarded bottles off the course in the area of the water station as possible. The majority of bottles will be dropped by runners within 500 metres.

Tie up full bags of rubbish. If you need more bags then please drop a call into the first aid point at the finish who will arrange for more to be sent to you.

Take regular breaks and swap round with other stewards so you are not stood doing the same job.

ENJOY IT! To runners, this is the most important part of their run, and the majority will be very grateful for your help.

## Event Profile

The event will attract a broad range of participants, typically aged between 15 and 75 years of age. Using experience gathered from previous events, abilities vary, but most are experienced or at least competed in a road race previously. The event information desk can offer advice as required as does the events website and the instruction sheet supplied to all competitors before the day (by email or post).

Sex Split: 70% men, 30% women.

Age Split: 10% 15-25, 15% 26-30, 45% 31-45, 20% 46-55, 10% 56+

Group: Single participants and Family groups

The event start time is: 11.05am

Arrival times for participants is between: 09.00am and 10.45am

Duration of the event is typically: 2 hours (10.30am – 12.30pm)

Set-Up of event starts at: 06.30am

Take-Down of event typically concludes at: 15.00pm

The main event is outdoors. The area used for registration, information and gathering is within the main carpark at Fairhaven Lake. The seasonal weather during the time of year is overcast with a significant risk of rain.

# Insurance

## UK Athletics Race Licence

The event is licensed under UK Athletics Rules. The following diagram shows the licence issued by UK Athletics for use on event day. The event is insured under this licence.

## Insurance Information & Policy Coverage

# Staff & Stewards

## Event Staff

### Core Staff

| Name | Position | Duty | Location | Contact |
| --- | --- | --- | --- | --- |
| Ron McAndrew | Race Director | Oversee event operations | Registration Lead Vehicle | 07854 763 016 |
| Lewis McAndrew | Event Safety Officer | Event Safety & Compliance | Registration Start & Finish Areas | 07768 639 409 |
| Alan Harrison | Event Manager | Setup of event facilities and equipment | Registration Start & Finish Areas | 07824 995680 |
| Tyler Harrison | Course Manager | Setup of course signage and water station delivery | Course | 07564 903 169 |
| Trish Harrison | Registration Manager | Oversee registration area and operations | Registration | 07913 017 430 |
| Joanne Tong | Steward Manager | Steward control and supervision | Course | 07941 364 290 |

### Registration

| Name | Position | Duty | Location | Times |
| --- | --- | --- | --- | --- |
| Trish Harrison | Registration Manager | Distribution of competitor race packs | Registration – Fairhaven Lake Café – Marquee | 0830hrs – 1050hrs |
| JT 1 | Registration Steward | Distribution of competitor race packs | Registration – Fairhaven Lake Café – Marquee | 0830hrs – 1050hrs |
| JT 2 | Registration Steward | Distribution of competitor race packs | Registration – Fairhaven Lake Café – Marquee | 0830hrs – 1050hrs |
| JT 3 | Registration Steward | Distribution of competitor race packs | Registration – Fairhaven Lake Café – Marquee | 0830hrs – 1050hrs |
| JT 4 | Registration Steward | Distribution of competitor race packs | Registration – Fairhaven Lake Café – Marquee | 0830hrs – 1050hrs |
| Kate Wildgoose | Late Registration / Enquiry Desk | Update computer list as required | Registration – Fairhaven Lake Café – Marquee | 0830hrs – 1050hrs |
| Ron McAndrew | Late Registration / Enquiry Desk | Update computer list as required | Registration – Fairhaven Lake Café – Marquee | 0830hrs – 1050hrs |

### Finish

| Name | Position | Duty | Location | Times |
| --- | --- | --- | --- | --- |
| Trish Harrison | Results | Timing iPad on finish line | Fairhaven Lake – Main car park (end) | 1100hrs – 1330hrs |
| Kate Wildgoose | Results | Timing iPad on finish line | Fairhaven Lake – Main car park (end) | 1100hrs – 1330hrs |
| Lewis McAndrew | Results | Recording iPad on finish funnel | Fairhaven Lake – Main car park (end) | 1100hrs – 1330hrs |
| JT 1 | Medals | Distribute Medals to finishers | Fairhaven Lake – Main car park (end) | 1100hrs – 1330hrs |
| JT 2 | Medals | Distribute Medals to finishers | Fairhaven Lake – Main car park (end) | 1100hrs – 1330hrs |
| JT 3 | Water | Distribute Water to finishers | Fairhaven Lake – Main car park (end) | 1100hrs – 1330hrs |
| JT 4 | Bananas | Distribute Bananas to finishers | Fairhaven Lake – Main car park (end) | 1100hrs – 1330hrs |

## Course Stewards

| Name | Location | Duty | Times |
| --- | --- | --- | --- |
| JT 5 | Fairhaven Lake – Main Car Park Entrance | Pass 1: Direct runners left out of car park onto Inner Promenade at start of race. Pass 2: Direct runners straight across car park entrance to continue along pathway on return from Windmill | 1100hrs – 1330hrs |
| JT 6 | St Pauls Avenue car park entrance | Pass 1: Direct runners left to run into car park on first pass Pass 2: Direct runners left to run into car park on first pass | 1100hrs – 1330hrs |
| JT 7 | End of St Pauls Avenue car park at start of Outer Promenade Pathway | Pass 1: Direct runners onto Outer Promenade Pathway Pass 2: Direct runners onto Outer Promenade Pathway | 1100hrs – 1330hrs |
| JT 8 | Ginnel entrance at Inner Promenade / Ansdell Road South | Pass 1: Direct runners right into ginnel to proceed along outer promenade towards Windmill. Pass 2: Direct runners left out of ginnel to proceed along outer promenade pathway back towards Fairhaven Lake. | 1100hrs – 1330hrs |
| JT 9 | Lytham Windmill | Pass 1: Runners pass the Windmill, running on the right hand side of the pathway Pass 2: Runners return from alongside the Windmill and turn right to run back along the Outer Promenade towards Fairhaven Lake | 1100hrs – 1330hrs |
| JT 10 | First pathway across Lytham Green after Windmill | Runners turn left onto pathway across Lytham Green | 1100hrs – 1330hrs |
| JT 11 | Turn off pathway onto grass | Runners turn left onto grass towards next pathway | 1100hrs – 1330hrs |
| JT 12 | Turn off grass onto pathway | Runners approach along grass to pathway and turn left towards the Windmill | 1100hrs – 1330hrs |

## Water Station Stewards

| Name | Location | Duty | Times |
| --- | --- | --- | --- |
| JT 13 | Lytham Green just passed Windmill at front of toilets | Distribute water bottles with cap removed to runners who require one. Collect discarded bottles from the course once runners have passed. | 1100hrs – 1330hrs |
| JT 14 | Lytham Green just passed Windmill at front of toilets | Distribute water bottles with cap removed to runners who require one. Collect discarded bottles from the course once runners have passed. | 1100hrs – 1330hrs |
| JT 15 | Lytham Green just passed Windmill at front of toilets | Distribute water bottles with cap removed to runners who require one. Collect discarded bottles from the course once runners have passed. | 1100hrs – 1330hrs |
| JT 16 | Lytham Green just passed Windmill at front of toilets | Distribute water bottles with cap removed to runners who require one. Collect discarded bottles from the course once runners have passed. | 1100hrs – 1330hrs |

# Course & Venue

## Venue Location

Fairhaven Lake Car Park

Inner Promenade

Lytham Saint Annes

FY8 1BD

Event marquees will be erected and removed on the day to facilitate the event registration areas and baggage storage.

## Start Location

The start is located at the Fairhaven Lake Car Park. The route to the start is clearly signed from the HQ and registration areas. A start banner will be located at the side of the start area to inform runners of the exact point. The start point is marked on the map below.

Runners will gather in the centre of the car park just prior to the start of the race. Runners will clear in approximately 5 minutes to allow full access to the car park.

## Finish Location

The finish is located at the end of the main Fairhaven Lake Car Park. The finish area will be enclosed using barriers/cones to create a safe area to distribute water, awards, and to administer first aid if necessary. An inflatable archway will be used to mark the finish location. The finish point is marked on the map below.

## Run Route

The run route starts at the main Fairhaven Lake Car Park and proceeds left out onto the Inner Promenade. The route then turns left into St Pauls Avenue Car Park. At the end of the car park the route proceeds onto the outer pathway behind the lake continuing round to Grannys Bay on the pavement. The route runs around Granny’s Bay to the right turn at Ansdell Road South ginnel to continue along the outer pathway towards Lytham Green. The route proceeds all the way along the outer pathway to Lytham Windmill before turning and following the same route back to the finish at Fairhaven Lake.

## Surface & Inspections

The surface of the entire route is a tarmac surface. The surface is of fairly good condition with no major potholes, cracks or defects that would prove to be of concern. There are some raised areas from tree routes, but “Uneven Surface” signs will be used as an advance warning. The route has been used in previous years for this event with no problems. Parts of the course have been re-tarmacked which eliminates this risk. The route has no works or planned works within the time of the event.

## Event Signage

Signage is important to give information to competitors and the public and to maintain a safe environment for runners, stewards, spectators and members of the general public. The course will be marked using arrows to show the route of the course. Each mile a sign will be used to mark the distance covered. Signs will also be used to advise the public that an event is in progress. Additional signs will be used to offer information to competitors. All the signs will be erected by the ESO. Most signs will be erected over 2.4m from the ground. In some cases signs will be mounted at floor level on road cones. All signage will be removed shortly after the event after the last runner has completed the route.

The signs that are used for the event are made from lightweight correx board and measure 24 inches by 18 inches. In most cases these signs are screwed to a small wooden stake to allow a good fixing onto street lights, signs or traffic cones. Where signs are installed on street lights or posts, they are erected over 2.4 metres to avoid contact with members of the public. They are attached using tie-wraps for a firm fixing. When attached to a traffic cone, duct tape is used and the high visibility aspect of the traffic cone is still visible.

## Aid Station

An Aid station for competitors will be located at three mile (halfway) on the route as recommended by UK Athletics Best Practice. Bottled water will be given out by stewards to everyone who requires them. Additional stewards will be responsible for collecting discarded bottles once used. The aid stations will be located just off the running line to avoid trips and falls. A sign will be placed 100 metres before the aid station as a warning to competitors. Tables will be used to hold the bottles before being handed out. All stewards will wear gloves and high visibility clothing. All bottle tops will be removed before handing to competitors.

## Car Parking

Parking is available using the existing car parks at Fairhaven Lake.

## Venue Information

The venue is made up of two event marquees, installed and removed on the day of the race by the event crew.

## Toilet Facilities

Temporary Toilets will be installed on the morning of the event and removed shortly afterwards. The units will be located at the end of the main Fairhaven Lake Car Park adjacent to the finish area.

The contractor for the temporary toilets is:

PORTABLE TOILET COMPANY

Shaw Farm
Stockclough Lane
Feniscowles
Blackburn
BB2 5JR

Phone: 01254 200181

# Risk Assessments

## General Event Risk Assessment

| GRA LINE CODE | Location / Hazard | People at Risk | Risk Rating Level (H/M/L) | Control Measures | Additional Measures & Checks | Risk Rating POST CONTROL Level (H/M/L) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Major incident on event day | Participants Spectators Event Staff Contractors | MED | Contingency plans as contained within this document |  | LOW |
| 2 | Major incident in build up period (e.g. Environmental Hazard) | Participants Spectators Event Staff Contractors | LOW | Event Planning Group exists for the event. Emergency session to be convened to define response in line with existing major incident plans | Regular liaison between Event Safety Officer and emergency services | LOW |
| 3 | Fire Risk at key assembly points (and event structures) | Participants Spectators Event Staff Contractors | MED | ESD contains fire procedures. LFRS aware of the event. Fire certification documents in place for all temporary structures | Event Safety Officer to ensure all fire regulations are adhered to | LOW |
| 4 | Duty of Medical Care: Staff in build up and strip out phases. Participants and spectators during the event | Participants Spectators Event Staff Contractors | MED | Event Safety Officer trained to EMT standard and on location for immediate callout during all periods Medical plan contained with ESD defining the levels of coverage on event day | Medical plan to be reviewed and assessed throughout the planning stages. | LOW |
| 5 | Major medical incident or fatality | Participants Spectators Event Staff Contractors | LOW | Medical plan contained with ESD defining the levels of coverage on event day Guidelines contained within the race licence criteria giving HSE advice | Medical plan to be reviewed and assessed throughout the planning stages. | LOW |
| 6 | Vehicle movement on site and on course sections | Participants Spectators Event Staff Contractors | LOW | Event designed with limited need to move vehicles during the event with all setup done before 0800hrs in the main start/finish area During the event stewards are to restrict vehicle movements from the general public. Vehicle passes to be issued to official cars on the route only | Event Safety Officer to monitor and manage emergency service access On-course medics to use pedal cycles to reduce vehicle movements | LOW |
| 7 | Traffic congestion and subsequent issues | Participants Spectators Event Staff Contractors Local Residents Non-event Traffic Business Users | MED | Mailshot to all local residents and businesses on the route and immediate vicinity of the route Advance signage in place 2 weeks before the event A number of businesses will be visited in person before the event IF APPLICABLE |  | LOW |
| 8 | Loss of stewarding personnel affecting implementation of closures | Participants Spectators Event Staff | LOW | Professional/reliable stewards used. Stewards regularly used at similar events. | Event Safety Officer to confirm attendance 48 and 24 hours before event | LOW |
| 9 | Loss of medical personnel affecting the delivery of the event | Participants Spectators Event Staff Contractors | LOW | Professional/reliable company used. Company regularly used at similar events. | Event Safety Officer to confirm attendance 48 and 24 hours before event | LOW |
| 10 | Supply of adequate drinking water to keep participants hydrated | Participants Spectators Event Staff Contractors | LOW | Bottled water puchased by FCR in advance of the event |  | LOW |
| 11 | Issues with power: Loss of supply and risk of electrocution | Participants Spectators Event Staff Contractors | LOW | Generator supply provided for PA systems at start/finish site Generator supplied with fuel tank and with plenty of reserve capacity Distribution carried by Speedy Hire | Site safety officer to check Electrician on standby | LOW |
| 12 | Power Supply for: PA system and timing equipment | Participants Spectators Event Staff Contractors | LOW | Generators to be placed with barriered compound Use of competent suppliers with risk assessment and health and safety policy to cover installation and operation Cable covers or matting to be used | Site safety officer to check Electrician on standby | LOW |
| 13 | Failure of PA systems | Participants Spectators Event Staff Contractors | LOW | Engineers from PA company on standby Loudhailer backup for keys areas | Tests on all equipment prior to the event Electrician on standby for power failures | LOW |
| 14 | Crowd disorder or unrest | Participants Spectators Event Staff Contractors | LOW | Use of PA, signage and stewards to keep participants and spectators informed (see ESD) Previous history of running event participants is that they are generally good natured |  | LOW |
| 15 | Incident from use of machinery / power tools in setup / breakdown | Event Staff Contractors | LOW | Only suitably qualified staff provided by event contractors will be permitted use of power tools or machinery No use of power tools to be required or permitted during public times on site |  | LOW |
| 16 | Manual movement of equipment on site | Event Staff Contractors | LOW | Safe system of work in place for staff covering manual handling Manual lifting to be limited where possible. Use of fork lifts, trollies or buggies as appropriate | Activities to be monitored by Event Safety Officer | LOW |
| 17 | Sanitary accommodation – problems arising from level of accommodation | Participants Spectators Event Staff Contractors | LOW | Installation of temporary facilities for the duration of the event. | Toilet provider to maintain. Personnel and equipment on site | LOW |
| 18 | Lost & found children / persons | Event Staff Participants | LOW | ESD details procedures in place for missing / found children |  | LOW |

## Course Risk Assessment

The following risk assessment is for the Windmill 10k Road Race. A degree of risk is inevitable in this type of event. Road runners should expect to encounter the following (up to a point); hard physical effort, adverse weather conditions, possible unevenness in running surfaces, jostling at the start point and the presence of other pedestrians.

Date of Assessment: 12 September 2016

Risk Assessment carried out by: Lewis McAndrew, Event Manager

| Course Section | Distance from start | Details of: General Information Hazard Road Conditions Junction | Risk Rating (H/M/L) | Persons at risk from described hazard | Measures taken to reduce risk to persons affected | Measures to be undertaken by | Risk Rating (H/M/L) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Start Section | 0km | Large gathering of competitors and spectators within Fairhaven Lake Main Car Park Surface:; Tarmac (Road). Condition:; Good. Damage:; Maintained. Traffic:; Car Park traffic. Junction:; n/a. | MED | Competitors Spectators General public Event Staff | Car park closed for approximately 15 minutes to allow gathering of runners for the start, then to proceed out at the start. ‘CAUTION RUNNERS’ signage located at car park entrance. | FCR Events Setup team | LOW |
| Inner Promenade | 0.05km – 0.84km | Runners on short road section Surface:; Tarmac (Road). Condition:; Good. Damage:; Maintained. Traffic:; General traffic. Junction:; Car Park to Car Park. | MED | Competitors Other road users | Rolling closure of traffic east to west to allow runners to leave car park and run west towards St Pauls Ave car park. Event safety vehicle to follow runners and use convoy method to safely control traffic. | Event Safety Officer | LOW |
| St Paul’s Avenue Car Park | 0.84km – 0.99km | Runners proceed through car park to outer pathway. Surface:; Tarmac. Condition:; Good. Damage:; Maintained. Traffic:; General traffic. Junction:; Car Park to Car Park. | LOW | Competitors Other road users | Runners proceed through centre of car park. Sheer bulk will proceed through quickly with little or no effect to car park traffic. Width of car park allows vehicle movement with care. ‘CAUTION RUNNERS’ signage located at car park entrance. |  | LOW |
| Outer Pathway | 0.99km – 2.33km | Runners proceed along outer pathway (staying on pathway) to the pathway ginnel past Granny’s Bay Surface:; Tarmac. Condition:; Good. Damage:; Maintained. Traffic:; Pedestrians. Junction:; n/a. | LOW | Competitors Other pavement users | Runners proceed along pathway. ‘CAUTION RUNNERS’ signage located at regular intervals. Lead Bicycle in use to warn pedestrians if necessary. |  | LOW |
| Outer Pathway | 2.33km – 5.19km | Runners proceed along outer pathway passing Lytham Green to Windmill. Surface:; Tarmac. Condition:; Good. Damage:; Maintained. Traffic:; Pedestrians. Junction:; n/a. | LOW | Competitors Other pavement users | Runners proceed along pathway. ‘CAUTION RUNNERS’ signage located at regular intervals. Lead Bicycle in use to warn pedestrians if necessary. |  | LOW |
| Grass section between pathways on Lytham Green | 5.19km – 5.6km | Runners proceed along grass section between the two pathways adjacent to Lytham Windmill. Surface:; Grass. Condition:; Level. Damage:; Maintained. Traffic:; none. Junction:; n/a. | LOW | Competitors | Runners proceed along pathway. ‘CAUTION RUNNERS’ signage located at regular intervals. Lead Bicycle in use to warn pedestrians if necessary. |  | LOW |
| Outer Pathway | 5.6km – 8.53km | Runners proceed along outer pathway passing Lytham Green back to Fairhaven Lake. Surface:; Tarmac. Condition:; Good. Damage:; Maintained. Traffic:; Pedestrians. Junction:; n/a. | LOW | Competitors Other pavement users | Runners proceed along pathway. ‘CAUTION RUNNERS’ signage located at regular intervals. Lead Bicycle in use to warn pedestrians if necessary. |  | LOW |
| Inner Promenade (Pathway) | 8.53km – 9.29km | Runners proceed along Inner Promenade pathway to St Pauls Ave car park. Surface:; Tarmac. Condition:; Good. Damage:; Maintained. Traffic:; Pedestrians. Junction:; n/a. | LOW | Competitors Other pavement users | Runners proceed along pathway. ‘CAUTION RUNNERS’ signage located at regular intervals. Lead Bicycle in use to warn pedestrians if necessary. |  | LOW |
| St Paul’s Avenue Car Park | 9.29km – 9.43km | Runners proceed through car park to outer pathway. Surface:; Tarmac. Condition:; Good. Damage:; Maintained. Traffic:; General traffic. Junction:; Car Park to Car Park. | LOW | Competitors Other road users | Runners proceed through centre of car park. Width of car park allows vehicle movement with care. ‘CAUTION RUNNERS’ signage located at car park entrance. |  | LOW |
| Outer Pathway | 9.43km – 10km | Runners proceed along outer pathway to finish at car park end. Surface:; Tarmac. Condition:; Good. Damage:; Maintained. Traffic:; Pedestrians. Junction:; n/a. | LOW | Competitors Other pavement users | Runners proceed along pathway. ‘CAUTION RUNNERS’ signage located at regular intervals. Lead Bicycle in use to warn pedestrians if necessary. |  | LOW |

## Medical Risk Assessment

The following medical risk assessment has been developed to fulfil the statutory duty of care to participants and staff working within the framework of the event. The following company is used to fulfil these requirements:

RMS AMBULANCE LTD (REMOTE MEDICAL SERVICES)
	TELEPHONE 07779 302 914

The following factors have been taken into consideration in preparing the assessment and event needs;

• Competitor numbers, profile and ages

• Course distance, severity and configuration

• Vehicular access for treatment and transportation of casualties (on course and finish areas)

• Proximity to local NHS A&E facility

• Past incident data

• Availability of communications

• Time of year, anticipated weather conditions

• Provision of drinking water, energy drinks, shelter etc.

Provision has been made for the treatment of the most common foreseeable injuries, including;

• Abrasions, cuts and sprains from trips and falls

• Head injuries from trips and falls

• Aggravation of pre-existing medical conditions including Asthma, Cardio-Vascular Disease and Diabetes

• Cardiac arrest

At the event planning stage consideration has been taken for the need for first-aid, extended medical provision and ambulance requirements. This will be supplied at appropriate levels for all stages of the event, including site build and breakdown periods.

| Area Assessed | Measures taken |
| --- | --- |
| Assessment of appropriate medical cover required for the event | Medical service coverage assessed in accordance the UK Athletics Good Practice Guide to Medical Services, exceeding where possible to the Event Safety Officers request and previous experience with this type of event. |
| Event arrangements and profile | The route has been used in previous years. The previous casualty and incident rate is MINIMAL. Closed roads with experience stewards and traffic management. |
| Anticipated competitor numbers | The event is likely to attract around 1000 competitors with approximately the same number with accompanying spectators. |
| Check availability of local NHS A&E facilities and Ambulance Trust | Hospital and Ambulance service notified via Planning Group in advance of the event. Nearest A&E facility approximately 3 miles from start/finish area of the event. |
| Ensure capability to deliver BLS plus AED response within 6 minutes of report of injury/incident by event stewards | Cycle responders on course trained and equipped to deliver BLS and AED. Course points identified to provide rapid response. Rear sweep vehicle and FAP at finish area to treat casualties and respond to incidents. |
| Procedures to check first aid in place before the start of the event | Medical Manager to report to Event Safety Officer, 4 hours before the event to confirm final arrangements are in place and confirmed. Medical Manager to call/meet Event Safety Officer on arrival to event to report in for duty. |
| Ensure effective reporting of casualties by stewards | Stewards deployed at regular intervals on the main route. All stewards are equipped with mobile phones or radio to contact the FAP at the finish area. All medics are equipped with mobile phone and radio. All stewards are briefed regarding reporting casualties to the FAP. |
| Layout and management of finish area to provide access for medical services | Finish area has a clear access lane. Finish area coordinator to ensure lane is free of general public and obstructions. |
| Public announcements | Pre-race announcements will be made to ensure rules and instructions are adhered to. To point out where medical facilities are located. Any participants who suffer from any significant health risk must put a large red cross on their run number to help medics respond accordingly. |
| Transport of exhausted runners | Medical team to oversee transport requirements for participants requiring it on the course. Any participant requiring transport will be transferred to the FAP for assessment. |
| Monitor | All communications between medics and event staff are monitored by the Medical Manager. All major incidents are to be reported to the Event Safety Officer. |

## Weather Risk Assessment

| WRA LINE CODE | Hazard | People at Risk | Risk Rating Level (H/M/L) | Control Measures | Additional Measures & Checks | Risk Rating POST CONTROL Level (H/M/L) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Extremes of hot and/or humid weather affecting welfare | Participants Spectators Event Staff Contractors | MED | Morning start is before the sun will have reached maximum levels Running produces a slight cooling breeze Ample stocks of water at drinks stations on the course. Announcements made to ensure runners take on water during the event | Constant monitoring by Event Safety Officer as to conditions on the day | LOW |
| 2 | Extremes of wet and/or cold/windy weather | Participants Spectators Event Staff Contractors | MED | Participants advised to stay wrapped up and wear appropriate clothing or the conditions (Social Media / Mass SMS if required) | Constant monitoring by Event Safety Officer as to conditions on the day | LOW |

# Medical Information

## Determined Medical Coverage

The following medical provision will be in place for the duration of the event including 45 minute stand-down time after the last runner has completed the event.

| 1 | Paramedic Ambulance for patient transfer and deployment on course if required | To be positioned and ready for use at 0830hrs |
| --- | --- | --- |
| 1 | Rapid Response Ambulance Car positioned on course at strategic location on course. To follow last runner in from halfway point if not in use | To be positioned and ready for use at 0945hrs |
| 3 | Cycle First Responders On patrol on course, following and looping the running field | To be positioned and ready for use at 0945hrs |
| 1 | Medical Tent Located within the finishing area. Beds included | To be positioned and ready for use at 0830hrs |

## Medical Personnel On Site

| Qty | Personnel | Location | Provider |
| --- | --- | --- | --- |
| 1 | Paramedic | Stationed in ambulance | Remote Medical Services |
| 1 | Nurse | Stationed at Med Tent | Remote Medical Services |
| 3 | ALS First Responders | On bikes on course | Remote Medical Services |
| 1 | Medical Manager | Course | Remote Medical Services |
| 2 | First Aider | Event Build Up and Breakdown – Event Safety Vehicle | FCR Events |

# Communications

## Event Communications Profile

Communication between all those involved in the delivery of the event on the day will be a key factor in ensuring that a safe and successful event takes place. The means of communication will vary from the use of a bespoke network of radio communication, mobile phones and word of mouth between individuals.

Key staff will be based at the start/finish areas and at the event registration/enquiry marquee. They will primarily make use of the radio network brought in for the event period.

## Event Radio Network

The network will be provided and installed by RMS AMBULANCE on the day of the event. Radios must be collected and signed for from the Medical Tent located at the start/finish area of the event.

# Event Specific Information

## Cancellation Policy

In the event that the Wigan 10k is cancelled prior to the start of the race on Sunday 6th September, the following plan will be brought into action (some actions, such as the mail out, will be dependant on the time available).

- Race Director to agree a public statement and short term action plan, including base for activity.

- Press statement to be put out to all participants.

- Press statement to be put out to website and social media.

- Social media platforms – Facebook and Twitter – to be updated by TF Marketing.

- Mass SMS to be sent by Joining Jack to all entrants, directing participants to www.fyldecoastrunners.org for further information.

- All participants – email to all entrants implemented by FCR admin staff.

- With a late announcement, event crew to be positioned at strategic points to meet any participants unaware of the situation.

- Press statement to follow on the next working day after the event – FCR to manage.

- Letters/emails to be sent to all participants within 3 days explaining the next steps – FCR to manage.

## Weather Information

The weather in Lytham is typical of northern weather, although in recent years, the summer months have been exceptionally sunny and the winters fairly mild. December, January and February tend to be Lythams coldest months, with average daytime temperature of 15 degress.

Lytham is said to have a moderate climate, which is typically northern. The wettest months in Lytham fall slightly earlier, between September and November, when you can expect approximately 110mm / 4.3 inches of precipitation every month. The overall rainfall is as its least in March, April and May, with just 56mm / 2. Inches expected each month, making these the towns driest months.

## Emergency Planning

DEFINITION
A major incident is any emergency that required the implementation of special arrangement by one or more of the emergency services, the NHS or the local authority for:

- The initial treatment, rescue and transport of a large number of casualties.

- The involvement either directly or indirectly of a large number of people.

- The handling of a large number of enquiries likely to be generated both from the public and the news media, usually to the police.

- The need for the large scale combined resources of two or more of the emergency services.

- The mobilisation and organisation of the emergency services and supporting organisations eg. Local authority, to cater for the threat of death, serious injury or homelessness to a large number of people.

The event is attended by over 1000 participants plus spectators on the day and so the risk of emergency incidents is present. In order to enable any emergency to be dealt with efficiently and safely, the following procedures are in place;

BOMB WARNING RECEIVED
If a bomb warning is received by the police, media or organisers, the following procedures will take place;

- If a location is specified in the warning, the Event Safety Officer and police are consulted. Any unusual packages or behaviour reported to the police and the area may be closed to the public. If a package is located, the police will investigate and take the necessary action in evacuation with the help of the Event Safety Officer and stewards.

- If no location is specified, a site meeting will be called with the Event Safety Officer, and a Police Liaison. The site meeting will take place in the Fairhaven Lake Cafe.

The procedures to follow will be directed by the police and could include a detailed search of all event areas, evacuation of all areas or partial evacuation of a particular area, and further investigation into the validity of the warning.

COMPLETE EVACUATION OF THE EVENT AREAS
If a complete evacuation of the town centre is required, the police will assist. An emergency meeting of all stewards will be called and the situation explained to them. Stewards will be responsible for moving all competitors, staff and spectators including event traders to the nearest egress route and clear the area. The event PA system will be used to give information to the public regarding the evacuation, the police will advise on the wording to be used. Once stewards have cleared the area, they will report to the Event Safety Officer who will ask them to stand by, evacuate or assist in another area. The Event Safety Officer will remain in constant communication with the police to ensure they are aware of the progress of the evacuation.

Participants will be stopped at the next available point on the course and will be prevented from re-entering the evacuated area until the situation has been fully assessed.

SUSPICIOUS PACKAGES
If a suspicious package is notified to a steward, they must contact the Event Safety Officer who will contact the police. The steward should be consulted as to any details they may have about the package and movements in the vicinity. The police will ascertain the seriousness of the package and may require partial evacuation, which will be conducted by the steward with the assistance of the police. The police will then proceed with the investigation.

FIRE
If a steward discovers a fire, they will raise the alarm by shouting. Evacuate all people that might be at risk. The steward will contact the emergency services by dialling 999 and then notify the Event Safety Officer or send someone to notify the Event Safety Officer. The Event Safety Officer will also notify the emergency services and then ensure that the police, event staff and Traffic Management Officer are aware and are expecting a fire engine. The police will ensure safe passage of the fire engine to the fire. The fire engine crew will deal with the fire as necessary.

Participants will be stopped at the next available point on the course and will be prevented from re-entering the evacuated area until the situation has been fully assessed.

HOSTILE AND NON HOSTILE DEMONSTRATIONS
If a demonstration takes place at the event location, either by an individual or a group, the stewards should notify the Event Safety Officer immediately. The Event Safety Officer will notify the police and a site meeting held to decide on the best course of action. It may be necessary for a steward to ask the individual to cease their actions and leave the event area, if they do not leave, the police will assist.

CRIMINAL INCIDENT
If a criminal incident occurs, the steward should notify the Event Safety Officer who will notify the police. If there is a direct risk to life then contact the police first then notify the Event Safety Officer or send someone to notify the Event Safety Officer. The police will deal with the situation in the appropriate manner and request a site meeting or evacuation.

ROAD INCIDENT
If an incident occurs on the roadways incorporating the event, the Event Safety Officer and police should be notified. The police will deal with the incident as quickly as possible and may re-route traffic as necessary. Stewards may be asked to help with re-routing or directing of the traffic.

EMERGENCY SITUATION
A pre-evacuation message will be notified to you from the Event Safety Officer. You should prepare for possible imminent evacuation.

The pre-evacuation message is: “All stewards operate a Code Black”.

If a full evacuation of your area is necessary, a public announcement will be made from the stage and/or PA system and/or you will be notified via radio or mobile phone from the Event Safety Officer.

The announcement will be: “Your attention please – for your own safety, please leave the event area by the exit directed by stewards”.

You must physically point and shout in the direction of safe exit during the evacuation. Your responsibility is to follow the instruction of the Event Safety Officer or emergency services in coordinating the evacuation. Once the evacuation is complete, and you are in a safe area, seal off the area and prevent re-admittance. Await further instructions.

## Lost Items/Property

Lost property will be difficult to locate due to the location and size of event. However, any item found at the start/finish areas will be taken to the event registration/enquiry marquee situated at the side of the Fairhaven Lake Cafe. Items will be booked in and not released until the claimant can provide an adequate description of the item. Where ownership cannot be proven or is contested, the matter will be passed to the police. Any valuable item left unclaimed at the end of the event will be handed to the police. All other property will be disposed of.

## Lost Children

The lost children point will be located within the event registration/enquiry marquee and will be staffed by CRB/DBS checked personnel for the duration of the event. If a lost child is found, the steward who finds them or is handed them should remain at the point in which the child was found for several minutes and then contact the Event Safety Officer, who will advise if the child has been reported missing or whether he/she should be taken to the lost children point as detailed above.

Details of the child’s location when found, clothing, age and description are ascertained and if the child can communicate, details of parents are asked from him/her and reported to the Event Safety Officer who will pass the information onto the lost children point. The Event Safety Officer will notify the police of the details and ask the PA announcer to announce that a child has been found and asking parents/guardians to report to the lost children point. Details and colour of the child’s coat/clothing is the only information that can be given out in the announcement.

- DO NOT REFER TO CHILDREN SPECIFICALLY OR GIVE DETAILS OF NAME, SEX OR AGE

Stewards will direct all members of the public who have either lost someone or are looking for someone to the lost children point. If a parent arrives looking for a child who is not there, use radios to circulate a description of the child to stewards. Upon the parent/guardian arriving to collect the missing person, they must be asked for the child’s name, age, sex and a description of the child’s clothing and this should be checked against the available information. Details of the person claiming the missing person will be noted down and given to the Event Safety Officer to record it officially. If there is any doubt as to the validity of the parent/guardian claim on the missing person, the police should be called and the matter dealt with by them. Missing persons not collected by the time the event closes, will be handed over to the police.

THE AIM OF THESE GUIDELINES IS TO PROTECT THE LOST CHILDREN AND EVENT STAFF FROM POSSIBLE LEGAL REPERCUSSIONS