# Event

# Safety

# Document

# Blackpool Music Run

# Sunday 16 June 2019

Table of Contents

Event Information	4

Introduction	4

Management & Planning	4

Local Authority Information	4

Event Profile	5

10k	5

5k	5

Policy Statements	6

Health & Safety Policy Statement	6

Equality Act 2010 Policy Statement	6

Children Act 1989/2004 Policy Statement	6

Course and Venue	7

Course Information	7

10k & 5k	7

Venue Information (Blackpool Music Run)	8

Surface & Inspections	8

Event Signage	8

Aid Station	8

Aid Station Locations	9

Car Parking	9

Toilet Facilities	9

Waste	9

Waster Carrier Registration	10

Staff & Stewards	11

Steward Responsibilities	11

Course Stewards	11

Water Station Stewards	11

Traffic Management Stewards	11

Event Staff & Stewards	13

Core Staff	13

Registration	13

Finish	13

Water Stations	13

Road Closure Stewards	14

Course Stewards	14

Insurance	15

UK Athletics Affiliation	15

UK Athletics Race Licence	15

Insurance Information & Policy Coverage	16

Evidence of Insurance Cover	17

Course Entertainment	20

Comedy Carpet Stage	20

Stage 1	20

Halfway Stage	20

Stage 3	20

Stage 4	20

Risk Assessments	21

General Event Risk Assessment	21

Course Risk Assessment	23

Medical Risk Assessment	24

Determined Medical Coverage	25

Medical Personnel On-Site	25

Weather Risk Assessment	25

Traffic Management	26

Summary	26

Advance Signage	26

Residents Letter	26

Traffic Management Plan	27

Emergency Event Planning	28

Cancellation Policy	28

Weather Information	28

Emergency Planning	28

DEFINITION	28

BOMB WARNING RECEIVED	28

COMPLETE EVACUATION OF THE EVENT AREAS	29

SUSPICIOUS PACKAGES	29

FIRE	29

HOSTILE AND NON-HOSTILE DEMONSTRATIONS	29

CRIMINAL INCIDENT	29

ROAD INCIDENT	29

EMERGENCY SITUATION	29

Lost Items/Property	30

Lost Children	30

Communications	31

Event Communications Profile	31

Event Radio Network	31

Appendix A	32

UK Athletics Event Adjudicator Form	32

Appendix B	34

Tramway Activity Permit	34

# Event Information

## Introduction

This document provides a summary of information for all aspects of the event, for the benefit of those involved in its organisation and delivery. This includes details of the event itinerary together with event personnel, site plans, routes, planning documents, schedules, risk assessment and cover provided by the medical services, stewards and emergency services.

The music run is a series of foot races consisting of:

- 5k Road Race (Blackpool Mini Music Run)

- 10k Road Race (Blackpool Music Run)

All officially measured, starting and finishing on the parade to the rear of the Metropole Hotel, Blackpool.

The event times are as follows:

- 5k – 11.00am

- 10k – 12.00pm

## Management & Planning

A number of key factors have been considered by FCR before promoting the event. The date has been checked as to not coincide with any similar event on the same day in the area using the events calendars at runbritain.com. The route, which has been used in previous years, was checked for access or any changes. The venue area has been checked whether the event can be hosted from there on the day. A preliminary risk assessment of the course has been undertaken to check suitability of the course. Checks have been made as to the availability of stewards and marshals on the day. Seasonal weather conditions have also been considered. After all these aspects have been considered, the event was proven to be acceptable and safe to promote.

## Local Authority Information

A notice of intention has been sent to Blackpool Council for consideration and approval from the Safety Advisory Group and/or all departments required to be informed of the event. The following departments/organisations have been informed about the event for pre-planning purposes:

• Blackpool Council forwarded to all relevant departments (via SAG)
• Blackpool Police (Events)
• Lancashire Ambulance Service (via SAG)
• Lancashire Fire & Rescue Service (via SAG)

• Blackpool, Fylde & Wyre Hospitals (via Remote Medical Services)

## Event Profile

The event will attract a broad range of participants. Using experience gathered from previous events, abilities vary, but most are experienced or at least competed in a road race previously. The event information desk can offer advice as required as does the events website and the instruction sheet supplied to all competitors before the day (by email).

### 10k

Sex Split: 55% men, 45% women.

Age Split: 10% 15-25, 15% 26-30, 45% 31-45, 20% 46-55, 10% 56+

Group: Single participants and Family groups

The event start time is: 12.00am

Arrival times for participants is between: 10.00am and 11.45am

Duration of the event is typically: 2 hours

Set-Up of event starts at: 5.00am

Take-Down of event typically concludes at: 5.00pm (conclusion of all the day’s running events)

### 5k

Sex Split: 55% men, 45% women.

Age Split: 8% 11-14, 5% 15-25, 15% 26-30, 42% 31-45, 20% 46-55, 10% 56+

Group: Single participants and Family groups

The event start time is: 11.00am

Arrival times for participants is between: 10.00am and 11.45am

Duration of the event is typically: 40 minutes

Set-Up of event starts at: 5.00am

Take-Down of event typically concludes at: 5.00pm (conclusion of all the day’s running events)

Both events are outdoors.

# Policy Statements

Health & Safety Policy Statement
FYLDE COAST RUNNERS on behalf HN TAYLOR (Blackpool Music Run)

It is an important duty of this organisation, in the conduct of its operations, to ensure a safe and healthy working environment for all its staff, stewards and volunteers. The organisation accepts the fact that this implies a corresponding duty of ensuring that necessary organisation, equipment and training is provided to fulfil this obligation. An effective health and safety policy requires the full collaboration and co-operation of all staff, stewards and volunteers; everybody is asked to read this policy and accept their own personal responsibility for health and safety at work.

It is the responsibility of the Event Manager:

a. to maintain the spirit and letter of the principles incorporated in the relevant legislation to ensure the safest systems of work and a safe, healthy working environment.

b. by consultation and joint involvement of management and staff, stewards and volunteers, to enlist the active interest, participation and support of staff, stewards and volunteers in promoting good standards.

It is the responsibility of all officials, stewards and volunteers:

a. to take all reasonable care for the health and safety of him/herself and of fellow staff, stewards and volunteers and to report any hazard which cannot be controlled personally.

b. to co-operate with the organisation by observing safety rules and complying with any measures designed to ensure a safe and healthy working environment.

The role of ‘Event Safety Officer (ESO)’ is of vital importance for maintaining a continuous and critical scrutiny of working conditions throughout the workplace, reviewing safety performance and promoting safer working. The designated ESO is the Event Manager. The Event Manager accepts ultimate responsibility for health and safety within the organisation as a whole. All staff, stewards and volunteers generally are expected to support and implement this policy wholeheartedly.

## Equality Act 2010 Policy Statement

FYLDE COAST RUNNERS on behalf HN TAYLOR (Blackpool Music Run)

As an organisation, Fylde Coast Running fully complies with the regulations and amendments contained within the Equality Act 2010. Specifically we recognise the protected characteristics of the following; Age, Disability, Gender Reassignment, Marriage and Civil Partnerships, Pregnancy and Maternity, Race, Religion or Beliefs, Sex and Sexual Orientation.

No aspect of the event compromises any of the Equality Act 2010 characteristics, and as an organisation uphold the values of all of the regulations and amendments. A copy of the Equality Act 2010 has been obtained and is available to view at the events office or public viewing or for reference by event staff.

## Children Act 1989/2004 Policy Statement

FYLDE COAST RUNNERS on behalf HN TAYLOR (Blackpool Music Run)

As an organisation, Fylde Coast Running fully complies with the regulations and amendments contained within the Children Act 1989/2004 and have taken the following pre-cautions to ensure a duty of care to minors. Minors under the age of 18 must have their entry form signed and dated by a parent or guardian. The medical services provider, Remote Medical Services, have all their personnel CRB checked. The event technical advisor and event manager are CRB checked.

No aspect of the event compromises any of the Children Act 1989/2004 and as an organisation uphold the values of all of the regulations and amendments. A copy of the Act has been obtained and is available to view at the events office or public viewing or for reference by event staff.

# Course and Venue

## Course Information

### 10k & 5k

- Start – Comedy Carpet (2 lap course for 10k) (1 lap for 5k)

- Proceed south from Comedy Carpet, crossing tram lines, then joining the main promenade at lamp column 260

- The route then proceeds south to a turning point just north of the Pleasure Beach at lamp column 409

- The route returns on the promenade, turning back in the for 5k at lamp column 260. The 10k turns back for a second lap then returns to the Comedy Carpet at lamp column 260.

## Venue Information (Blackpool Music Run)

Event marquees will be erected and removed on the day to facilitate the event registration areas and baggage storage. Toilets will also be installed and removed on the day of the event. No equipment or facilities will be left unattended overnight on the parade or on the course/promenade.

## Surface & Inspections

The surface of the entire route is a tarmac/concrete surface. The surface is of fairly good condition with no major potholes, cracks or defects that would prove to be of concern. The route has been used in previous years for numerous events with no significant issues. The route has no works or planned works within the time of the event.

## Event Signage

Signage is important to give information to competitors and the public and to maintain a safe environment for runners, stewards, spectators and members of the general public. The course will be marked using arrows to show the route of the course. Each mile a sign will be used to mark the distance covered. Signs will also be used to advise the public that an event is in progress. Additional signs will be used to offer information to competitors. All the signs will be erected by the FCR event crew. Most signs will be erected over 2.4m from the ground. In some cases, signs will be mounted at floor level on road cones or on quick frames. All signage will be removed shortly after the event after the last runner has completed the route.

The signs that are used for the event are made from lightweight correx board and measure 24 inches by 18 inches. In most cases these signs are screwed to a small wooden stake to allow a good fixing onto street lights, signs or traffic cones. Where signs are installed on street lights or posts, they are erected over 2.4 metres to avoid contact with members of the public. They are attached using tie-wraps for a firm fixing. When attached to a traffic cone, duct tape is used, and the high visibility aspect of the traffic cone is still visible.

## Aid Station

Aid stations for competitors will be located at various locations on the routes as recommended by UK Athletics Best Practice. Bottled water will be given out by stewards to everyone who requires them. Additional stewards will be responsible for collecting discarded bottles once used. The aid stations will be located just off the running line to avoid trips and falls. A sign will be placed 100 metres before the aid station as a warning to competitors. Tables will be used to hold the bottles before being handed out. All stewards will wear gloves and high visibility clothing. All bottle tops will be removed before handing to competitors.

## Aid Station Locations

10k		• Balmoral Road area at southern turning point.

## Car Parking

There is no dedicated parking facilities for the event. Competitors are advised to use pre-existing facilities in the town centre and central car parks.

## Toilet Facilities

Temporary Toilets will be installed on each morning of the events and removed shortly afterwards. The units will be located adjacent to the registration area on the Middle Walkway.

The contractor for the temporary toilets is:

PORTABLE TOILET COMPANY

Shaw Farm, Stockclough Lane, Feniscowles, Blackburn BB2 5JR

Phone: 01254 200181

## Waste

All waste generated will be bagged and transferred to FCR HQ for collection by Biffa under our current waste contract. All medical waste will be controlled by Remote Medical Services.

## Waster Carrier Registration

# Staff & Stewards

## Steward Responsibilities

### Course Stewards

The main responsibilities of the stewards are to act as markers on the course and to provide safety for runners in that area of the course. They will also assist the police and other emergency services should the need arise. Stewards are also required to report any injuries or runners requiring medical assistance.

Whilst on duty, stewards will:

Concentrate only on their duties. Not use mobile phones, iPods or other electronic devices unless required to report an emergency or medical assistance request to the First Aid Point.

Not leave their place without permission unless told to do so by the Event Manager or Police.

Not consume or be under the influence of alcohol or drugs.

Remain calm and be courteous towards members of the public and runners.

Wear distinctive hi-visibility clothing at all times.

Be familiar with the course to direct runners and answer any relevant questions.

Be prepared to assist in other areas of the event if the need arises.

Be responsible and over the age of 18.

Stewards will be required to stand at their designated point for quite some time. We advise that they wear clothing appropriate for the time of year and have a flask of warm drink or drinks bottles. We also advise a trip to the toilet before the start of the race. If a steward wants to leave post at any time during the event, they must call in to the first aid point to have a replacement steward sent to their point. STEWARDS ARE NOT TO LEAVE THEIR POINT UNATTENDED UNDER ANY CIRCUMSTANCES. On the day of the events, all stewards and supervisors will be walked or driven onto the route after being briefed on their specific role.

### Water Station Stewards

The main responsibilities of the stewards are to distribute bottled water to runners from their designated point. They will also assist the police and other emergency services should the need arise. Water Station Stewards are also required to report any injuries or runners requiring medical assistance.

Stewards will be required to stand at their designated point for quite some time. We advise that they wear clothing appropriate for the time of year and have a flask of warm drink or drinks bottles. We also advise a trip to the toilet before the start of the race. If a steward wants to leave post at any time during the event, they must call in to the first aid point to have a replacement steward sent to their point. STEWARDS ARE NOT TO LEAVE THEIR POINT UNATTENDED UNDER ANY CIRCUMSTANCES.

Water Station Best Practice

Please remove the bottle tops before handing to the runner. Throw bottle tops in the bags provided. Place enough opened bottles on the table to help you grab them when it gets busy and the runner’s approach in groups. Collect as many discarded bottles off the course in the area of the water station as possible. The majority of bottles will be dropped by runners within 500 metres. Tie up full bags of rubbish. If you need more bags, then please drop a call into the first aid point at the finish who will arrange for more to be sent to you. Take regular breaks and swap round with other stewards so you are not stood doing the same job. ENJOY IT! To runners, this is the most important part of their run, and the majority will be very grateful for your help.

### Traffic Management Stewards

The main responsibilities of the traffic management stewards are to uphold the road closure order, advise motorists of alternative routes and to provide safety for runners and members of the public where they are positioned. They will also assist the police and other emergency services should the need arise. Stewards are also required to report any injuries or runners requiring medical assistance.

Whilst on duty, stewards will:

Concentrate only on their duties. Not use mobile phones, iPods or other electronic devices unless required to report an emergency or medical assistance request to the First Aid Point.

Not leave their place without permission unless told to do so by the Event Manager or Police.

Not consume or be under the influence of alcohol or drugs.

Remain calm and be courteous towards members of the public and runners.

Wear distinctive hi-visibility clothing at all times.

Be familiar with the course to direct runners and answer any relevant questions.

Be prepared to assist in other areas of the event if the need arises.

Be responsible and over the age of 18.

Stewards will be required to stand at their designated point for quite some time. We advise that they wear clothing appropriate for the time of year and have a flask of warm drink or drinks bottles. We also advise a trip to the toilet before the start of the race. If a steward wants to leave post at any time during the event, they must call in to the first aid point to have a replacement steward sent to their point. STEWARDS ARE NOT TO LEAVE THEIR POINT UNATTENDED UNDER ANY CIRCUMSTANCES. On the day of the events, all stewards and supervisors will be walked or driven onto the route after being briefed on their specific role.

## Event Staff & Stewards

### Core Staff

| Name | Position | Duty | Location | Contact |
| --- | --- | --- | --- | --- |
| Luke Taylor | Race Director | Oversee event operations | Registration Lead Vehicle |  |
| Lewis McAndrew | Event Safety Officer | Event Safety & Compliance | Registration Start & Finish Areas | 07488 275 276 |
| Alan Harrison | Event Manager | Setup of event facilities and equipment | Registration Start & Finish Areas | 07824 995680 |
| Tyler Harrison | Traffic & Course Manager | Setup of course signage and water station delivery | Course | 07564 903 169 |
| Trish Harrison | Registration Manager | Oversee registration area and operations | Registration | 07913 017 430 |
| Joanne Tong | Steward Manager | Steward control and supervision | Course | 07941 364 290 |
| Brian Porter | UK Athletics Event Adjudicator | Ensure event is operated and run under given standards | Start & Finish Areas |  |

### Registration

| Name | Position | Duty | Location | Times |
| --- | --- | --- | --- | --- |
| Trish Harrison | Registration Manager | Distribution of competitor race packs | Registration | 0900hrs – 1200hrs |
| *Volunteer* | Registration Steward | Distribution of competitor race packs | Registration | 0900hrs – 1200hrs |
| *Volunteer* | Registration Steward | Distribution of competitor race packs | Registration | 0900hrs – 1200hrs |
| *Volunteer* | Registration Steward | Distribution of competitor race packs | Registration | 0900hrs – 1200hrs |
| *Volunteer* | Registration Steward | Distribution of competitor race packs | Registration | 0900hrs – 1200hrs |
| *Volunteer* | Registration Steward | Distribution of competitor race packs | Registration | 0900hrs – 1200hrs |
| *Volunteer* | Late Registration / Enquiry Desk | Update computer list as required | Registration | 0900hrs – 1200hrs |
| *Volunteer* | Late Registration / Enquiry Desk | Update computer list as required | Registration | 0900hrs – 1200hrs |

### Finish

| Name | Position | Duty | Location | Times |
| --- | --- | --- | --- | --- |
| Trish Harrison | Management | Control Area | Finish Line |  |
| Lewis McAndrew | Results | Chip Timing | Finish Line |  |
| *Volunteer* | Medals | Distribute Medals | Finish Line | 1100hrs – 1400hrs |
| *Volunteer* | Medals | Distribute Medals | Finish Line | 1100hrs – 1400hrs |
| *Volunteer* | Water | Distribute Water | Finish Line | 1100hrs – 1400hrs |
| *Volunteer* | Water | Distribute Water | Finish Line | 1100hrs – 1400hrs |
| *Volunteer* | Bananas | Distribute Bananas | Finish Line | 1100hrs – 1400hrs |

### Water Stations

| STATION ID | GROUP | LOCATION | EQUIPMENT | TIME ON | TIME OFF |
| --- | --- | --- | --- | --- | --- |
| Halfway (5k) | *Volunteer* x5 | Abercorn Place | 3 Tables Bin Bags, Gloves, Hand Gel *** BOTTLES | 1130hrs | 1300HRS |

### Road Closure Stewards

| STEWARD ID | NAME / GROUP | LOCATION | DUTY | TIME ON | TIME OFF |
| --- | --- | --- | --- | --- | --- |
|  | FCR Traffic Management | Burlington Rd West – TOTAL CLOSURE | No Marshal Required | 11.00am | 1.45pm |
| BMR-TM-009 | TM Steward | Burlington Road West | Uphold Road Closure | 11.00am | 1.45pm |
| BMR-TM-010 | TM Steward | Clifton Drive | Uphold Road Closure | 11.00am | 1.45pm |
| BMR-TM-011 | TM Steward | Watson Road (if re-opened) | Uphold Road Closure | 11.00am | 1.45pm |
| BMR-TM-012 | TM Steward | Balmoral Road | Uphold Road Closure | 11.00am | 1.45pm |
| BMR-TM-013 | TM Steward | Osborne Road | Uphold Road Closure | 11.00am | 1.45pm |
| BMR-TM-014 | TM Steward | Withnell Road | Uphold Road Closure | 11.00am | 1.45pm |
| BMR-TM-015 | TM Steward | Station Road | Uphold Road Closure | 11.00am | 1.45pm |
| BMR-TM-016 | TM Steward | Dean Street | Uphold Road Closure | 11.00am | 1.45pm |
| BMR-TM-017 | TM Steward | Rawcliffe Street | Uphold Road Closure | 11.00am | 1.45pm |
| BMR-TM-018 | TM Steward | Waterloo Road | Uphold Road Closure | 11.00am | 1.45pm |
| BMR-TM-019 | TM Steward | Commercial Street | Uphold Road Closure | 11.00am | 1.45pm |
| BMR-TM-020 | TM Steward | Britannia Place | Uphold Road Closure | 11.00am | 1.45pm |
| BMR-TM-021 | TM Steward | Shaw Road | Uphold Road Closure | 11.00am | 1.45pm |
| BMR-TM-022 | TM Steward | Alexandra Road | Uphold Road Closure | 11.00am | 1.45pm |
| BMR-TM-023 | TM Steward | Crystal Road | Uphold Road Closure | 11.00am | 1.45pm |
| BMR-TM-024 | TM Steward | St Chad’s Road | Uphold Road Closure | 11.00am | 1.45pm |
| BMR-TM-025 | TM Steward | Woodfield Road | Uphold Road Closure | 11.00am | 1.45pm |
| BMR-TM-026 | TM Steward | Wellington Road | Uphold Road Closure | 11.00am | 1.45pm |
| BMR-TM-027 | TM Steward | Barton Avenue | Uphold Road Closure | 11.00am | 1.45pm |
| BMR-TM-028 | TM Steward | Trafalgar Road | Uphold Road Closure | 11.00am | 1.45pm |
| BMR-TM-029 | TM Steward | Lytham Road at junction with Tyldesley Road | Uphold Road Closure | 11.00am | 1.45pm |
| BMR-TM-030 | TM Steward | Rigby Road at junction with Tyldesley Road | Uphold Road Closure | 11.00am | 1.45pm |
| BMR-TM-031 | TM Steward | Foxhall Square | Uphold Road Closure | 11.00am | 1.45pm |
| BMR-TM-032 | TM Steward | Bairstow Street | Uphold Road Closure | 11.00am | 1.45pm |
| BMR-TM-033 | TM Steward | Yorkshire Street | Uphold Road Closure | 11.00am | 1.45pm |
| BMR-TM-034 | TM Steward | Chapel Street at junction with Bonny Street | Uphold Road Closure | 11.00am | 1.45pm |
| BMR-TM-035 | TM Steward | New Bonny Street at junction with Bonny Street | Uphold Road Closure | 11.00am | 1.45pm |
| BMR-TM-036 | TM Steward | Church Street at junction with Market Street | Uphold Road Closure | 11.00am | 1.45pm |
|  | FCR Traffic Management | Promenade junction with Springfield Road – TOTAL CLOSURE | No Marshal Required | 11.00am | 1.45pm |

### Course Stewards

| STEWARD ID | NAME / GROUP | LOCATION | DUTY | TIME ON | TIME OFF |
| --- | --- | --- | --- | --- | --- |
|  | Blackpool Transport Ltd. | Gynn Crossing Supervisor/Conductor | Control tram movements | 1150hrs | 1330hrs |
| BMR-CS-054 | *Volunteer* | Assist at tramway crossing point (with Blackpool Transport) | Assist BTS | 1200hrs | 1330hrs |
| BMR-CS-055 | *Volunteer* | Just after tramway crossing on Promenade | Direct runners on correct route | 1200hrs | 1330hrs |
| BMR-CS-056 | *Volunteer* | Turn point at South Shore | Direct runners on correct route | 1200hrs | 1330hrs |

# Insurance

## UK Athletics Affiliation

Fylde Coast Runners is registered and affiliated to UK Athletics as a club, Affiliation Number: 7692524

## UK Athletics Race Licence

The event is licensed under UK Athletics Rules. The following diagram shows the licence issued by UK Athletics for use on event day. The event is insured under this licence.

*** Licence applied for

## Insurance Information & Policy Coverage

## Evidence of Insurance Cover

# Risk Assessments

## General Event Risk Assessment

| GRA LINE CODE | Location / Hazard | People at Risk | Risk Rating Level (H/M/L) | Control Measures | Additional Measures & Checks | Risk Rating POST CONTROL Level (H/M/L) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Major incident on event day | Participants Spectators Event Staff Contractors | MED | Contingency plans as contained within this document |  | LOW |
| 2 | Major incident in build up period (e.g. Environmental Hazard) | Participants Spectators Event Staff Contractors | LOW | Event Planning Group exists for the event. Emergency session to be convened to define response in line with existing major incident plans | Regular liaison between Event Safety Officer and emergency services | LOW |
| 3 | Fire Risk at key assembly points (and event structures) | Participants Spectators Event Staff Contractors | MED | ESD contains fire procedures. LFRS aware of the event. Fire certification documents in place for all temporary structures | Event Safety Officer to ensure all fire regulations are adhered to | LOW |
| 4 | Duty of Medical Care: Staff in build up and strip out phases. Participants and spectators during the event | Participants Spectators Event Staff Contractors | MED | Event Safety Officer trained to EMT standard and on location for immediate callout during all periods Medical plan contained with ESD defining the levels of coverage on event day | Medical plan to be reviewed and assessed throughout the planning stages. | LOW |
| 5 | Major medical incident or fatality | Participants Spectators Event Staff Contractors | LOW | Medical plan contained with ESD defining the levels of coverage on event day Guidelines contained within the race licence criteria giving HSE advice | Medical plan to be reviewed and assessed throughout the planning stages. | LOW |
| 6 | Vehicle movement on site and on course sections | Participants Spectators Event Staff Contractors | LOW | Event designed with limited need to move vehicles during the event with all setup done before 0800hrs in the main start/finish area During the event stewards are to restrict vehicle movements from the general public. Vehicle passes to be issued to official cars on the route only | Event Safety Officer to monitor and manage emergency service access On-course medics to use pedal cycles to reduce vehicle movements | LOW |
| 7 | Traffic congestion and subsequent issues | Participants Spectators Event Staff Contractors Local Residents Non-event Traffic Business Users | MED | Mailshot to all local residents and businesses on the route and immediate vicinity of the route Advance signage in place 2 weeks before the event A number of businesses will be visited in person before the event IF APPLICABLE |  | LOW |
| 8 | Loss of stewarding personnel affecting implementation of closures | Participants Spectators Event Staff | LOW | Professional/reliable stewards used. Stewards regularly used at similar events. | Event Safety Officer to confirm attendance 48 and 24 hours before event | LOW |
| 9 | Loss of medical personnel affecting the delivery of the event | Participants Spectators Event Staff Contractors | LOW | Professional/reliable company used. Company regularly used at similar events. | Event Safety Officer to confirm attendance 48 and 24 hours before event | LOW |
| 10 | Supply of adequate drinking water to keep participants hydrated | Participants Spectators Event Staff Contractors | LOW | Bottled water puchased by FCR in advance of the event |  | LOW |
| 11 | Issues with power: Loss of supply and risk of electrocution | Participants Spectators Event Staff Contractors | LOW | Generator supply provided for PA systems at start/finish site Generator supplied with fuel tank and with plenty of reserve capacity Distribution carried by Speedy Hire | Site safety officer to check Electrician on standby | LOW |
| 12 | Power Supply for: PA system and timing equipment | Participants Spectators Event Staff Contractors | LOW | Generators to be placed with barriered compound Use of competent suppliers with risk assessment and health and safety policy to cover installation and operation Cable covers or matting to be used | Site safety officer to check Electrician on standby | LOW |
| 13 | Failure of PA systems | Participants Spectators Event Staff Contractors | LOW | Engineers from PA company on standby Loudhailer backup for keys areas | Tests on all equipment prior to the event Electrician on standby for power failures | LOW |
| 14 | Crowd disorder or unrest | Participants Spectators Event Staff Contractors | LOW | Use of PA, signage and stewards to keep participants and spectators informed (see ESD) Previous history of running event participants is that they are generally good natured |  | LOW |
| 15 | Incident from use of machinery / power tools in setup / breakdown | Event Staff Contractors | LOW | Only suitably qualified staff provided by event contractors will be permitted use of power tools or machinery No use of power tools to be required or permitted during public times on site |  | LOW |
| 16 | Manual movement of equipment on site | Event Staff Contractors | LOW | Safe system of work in place for staff covering manual handling Manual lifting to be limited where possible. Use of fork lifts, trollies or buggies as appropriate | Activities to be monitored by Event Safety Officer | LOW |
| 17 | Sanitary accommodation – problems arising from level of accommodation | Participants Spectators Event Staff Contractors | LOW | Installation of temporary facilities for the duration of the event. | Toilet provider to maintain. Personnel and equipment on site | LOW |
| 18 | Lost & found children / persons | Event Staff Participants | LOW | ESD details procedures in place for missing / found children |  | LOW |

## Course Risk Assessment

The following risk assessment is for the Blackpool Music Run. A degree of risk is inevitable in this type of event. Road runners should expect to encounter the following (up to a point); hard physical effort, adverse weather conditions, possible unevenness in running surfaces, jostling at the start point and the presence of other pedestrians and road users.

Date of Assessment: 6 July 2018

Risk Assessment carried out by: Lewis McAndrew, Event Safety Officer

| Course Section | Miles from Start | Details of Risk / Road Conditions / Junction / Risk | Pre-Risk Assessment Rating (H/M/L) | Persons at risk from hazard | Measures taken to reduce risk to persons affected | Measures undertaken by and enforced by | Additional information | Post-Risk Assessment Rating (H/M/L) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Route to Start | 0 | Competitors and spectators leaving the registration area to go to the start area. | L | Competitors, Spectators | The route to the start will be clearly signed including an archway/gantry over the start line to show the exact start location. | Event Signage Event Safety Officer Event Manager |  | L |
| Start Area | 0 | Large gathering of runners on parade waiting to start the race. Runners straying onto tramway. | M | Competitors | Road closure in force on the promenade. Barriers used to prevent runners straying onto the tramway. | FCR |  | L |
| Tramway Crossing | 0.3-0.3 km | Crossing of tramway to main promenade | H | Competitors | Blackpool Transport Services conductor in place to control flow of trams on a stop/go principle | BTS Event Safety Officer |  | L |
| Promenade | 0.3-9.89 km | Runners on promenade | M | Competitors | Total road closure from Springfield Road to Starr Gate for the duration of the event. | FCR TM Stewards on all road ends |  | L |
| Pathway running alongside gardens (Upper Walkway) | 7.10 Miles | Runners proceeding along a narrow section of pathway with members of the public also present. This section is on tarmac surface. The surface is smooth with no significant defects, cracks or potholes that need to be addressed. | M | Competitors and Members of the Public | The area is signed with marker arrow and Event in Progress to advise members of the public about the event and to proceed with caution. Advisory signs will be deployed to use the gardens as an alternative route for pedestrians. | Event Safety Officer |  | L |
| Tramway Crossing | 9.89-9.89 km | Crossing of tramway to main promenade | H | Competitors | Blackpool Transport Services conductor in place to control flow of trams on a stop/go principle | BTS Event Safety Officer |  | L |

## Medical Risk Assessment

The following medical risk assessment has been developed to fulfil the statutory duty of care to participants and staff working within the framework of the event. The following company is used to fulfil these requirements:

RMS AMBULANCE LTD (REMOTE MEDICAL SERVICES)
	TELEPHONE 07779 302 914

The following factors have been taken into consideration in preparing the assessment and event needs;

• Competitor numbers, profile and ages

• Course distance, severity and configuration

• Vehicular access for treatment and transportation of casualties (on course and finish areas)

• Proximity to local NHS A&E facility

• Past incident data

• Availability of communications

• Time of year, anticipated weather conditions

• Provision of drinking water, energy drinks, shelter etc.

Provision has been made for the treatment of the most common foreseeable injuries, including;

• Abrasions, cuts and sprains from trips and falls

• Head injuries from trips and falls

• Aggravation of pre-existing medical conditions including Asthma, Cardio-Vascular Disease and Diabetes

• Cardiac arrest

At the event planning stage consideration has been taken for the need for first-aid, extended medical provision and ambulance requirements. This will be supplied at appropriate levels for all stages of the event, including site build and breakdown periods.

| Area Assessed | Measures taken |
| --- | --- |
| Assessment of appropriate medical cover required for the event | Medical service coverage assessed in accordance the UK Athletics Good Practice Guide to Medical Services, exceeding where possible to the Event Safety Officers request and previous experience with this type of event. |
| Event arrangements and profile | The route has been used in previous years. The previous casualty and incident rate is MINIMAL. Closed roads with experience stewards and traffic management. |
| Anticipated competitor numbers | The event is likely to attract around 1000 competitors with approximately the same number with accompanying spectators. |
| Check availability of local NHS A&E facilities and Ambulance Trust | Hospital and Ambulance service notified via Planning Group in advance of the event. Nearest A&E facility approximately 12 miles from start/finish area of the event. |
| Ensure capability to deliver BLS plus AED response within 6 minutes of report of injury/incident by event stewards | Cycle responders on course trained and equipped to deliver BLS and AED. Course points identified to provide rapid response. Rear sweep vehicle and FAP at finish area to treat casualties and respond to incidents. |
| Procedures to check first aid in place before the start of the event | Medical Manager to report to Event Safety Officer, 4 hours before the event to confirm final arrangements are in place and confirmed. Medical Manager to call/meet Event Safety Officer on arrival to event to report in for duty. |
| Ensure effective reporting of casualties by stewards | Stewards deployed at regular intervals on the main route. All stewards are equipped with mobile phones or radio to contact the FAP at the finish area. All medics are equipped with mobile phone and radio. All stewards are briefed regarding reporting casualties to the FAP. |
| Layout and management of finish area to provide access for medical services | Finish area has a clear access lane. Finish area coordinator to ensure lane is free of general public and obstructions. |
| Public announcements | Pre-race announcements will be made to ensure rules and instructions are adhered to. To point out where medical facilities are located. Any participants who suffer from any significant health risk must put a large red cross on their run number to help medics respond accordingly. |
| Transport of exhausted runners | Medical team to oversee transport requirements for participants requiring it on the course. Any participant requiring transport will be transferred to the FAP for assessment. |
| Monitor | All communications between medics and event staff are monitored by the Medical Manager. All major incidents are to be reported to the Event Safety Officer. |

## Determined Medical Coverage

The following medical provision will be in place for the duration of the event including 45 minute stand-down time after the last runner has completed the event.

| 1 | Paramedic Ambulance for patient transfer and deployment on course if required | To be positioned and ready for use at 1000hrs |
| --- | --- | --- |
| 1 | Rapid Response Ambulance Car positioned on course at strategic location on course. To follow last runner in from halfway point if not in use | To be positioned and ready for use at 1000hrs |
| 3 | Cycle First Responders On patrol on course, following and looping the running field | To be positioned and ready for use at 1000hrs |
| 1 | Medical Tent Located within the finishing area. Beds included | To be positioned and ready for use at 1000hrs |

## Medical Personnel On-Site

| Qty | Personnel | Location | Provider |
| --- | --- | --- | --- |
| 2 | Paramedic | Stationed in ambulance | Remote Medical Services |
| 1 | Nurse | Stationed at Med Tent | Remote Medical Services |
| 3 | ALS First Responders | On bikes on course | Remote Medical Services |
| 1 | Medical Manager | Course | Remote Medical Services |
| 3 | First Aider | Event Build Up and Breakdown – Event Safety Vehicle | FCR Events |

## Weather Risk Assessment

| WRA LINE CODE | Hazard | People at Risk | Risk Rating Level (H/M/L) | Control Measures | Additional Measures & Checks | Risk Rating POST CONTROL Level (H/M/L) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Extremes of hot and/or humid weather affecting welfare | Participants Spectators Event Staff Contractors | MED | Morning start is before the sun will have reached maximum levels Running produces a slight cooling breeze Ample stocks of water at drinks stations on the course. Announcements made to ensure runners take on water during the event | Constant monitoring by Event Safety Officer as to conditions on the day | LOW |
| 2 | Extremes of wet and/or cold/windy weather | Participants Spectators Event Staff Contractors | MED | Participants advised to stay wrapped up and wear appropriate clothing or the conditions (Social Media / Mass SMS if required) | Constant monitoring by Event Safety Officer as to conditions on the day | LOW |

# Traffic Management

To facilitate the safe running of the event on the highway, a road closure will be operational.

## Summary

Closure of promenade from Springfield Road to Burlington Road West. Operational from 1030hrs until 1400hrs on Sunday 16 June 2019. Diversion routes will be the pre-installed ‘circle’ and ‘diamond’ routes. Additional signage will be used around the Springfield Road area to pick up the diversion routes.

## Advance Signage

Signs will be installed on all major routes onto the Promenade advising of the closure two weeks in advance. These will be installed and maintained by FCR.

## Residents Letter

A letter will be hand delivered to all premises on the Promenade including premises west of the tramway. The letter will be distributed two weeks in advance.

## Traffic Management Plan

# Emergency Event Planning

## Cancellation Policy

In the event that the Blackpool Music Run is cancelled prior to the start of the race on Sunday 23rd September 2018, the following plan will be brought into action (some actions, such as the mail out, will be dependent on the time available).

- Race Director to agree a public statement and short-term action plan, including base for activity.

- Press statement to be put out to all participants.

- Press statement to be put out to website and social media.

- Social media platforms – Facebook and Twitter – to be updated by FCR.

- Mass SMS to be sent by FCR to all entrants, directing participants to www.blackpoolmusicrun.co.uk for further information.

- All participants – email to all entrants implemented by FCR admin staff.

- With a late announcement, event crew to be positioned at strategic points to meet any participants unaware of the situation.

- Press statement to follow on the next working day after the event – FCR to manage.

- Letters/emails to be sent to all participants within 3 days explaining the next steps – FCR to manage.

## Weather Information

The weather in Blackpool is typical of northern weather, although in recent years, the summer months have been exceptionally sunny and the winters fairly mild. December, January and February tend to be Blackpool’s coldest months, with average daytime temperature of 15 degrees.

Blackpool is said to have a moderate climate, which is typically northern. The wettest months in Blackpool fall slightly earlier, between September and November, when you can expect approximately 110mm / 4.3 inches of precipitation every month. The overall rainfall is as its least in March, April and May, with just 56mm / 2. Inches expected each month, making these the towns driest months.

## Emergency Planning

DEFINITION
A major incident is any emergency that required the implementation of special arrangement by one or more of the emergency services, the NHS or the local authority for:

- The initial treatment, rescue and transport of a large number of casualties.

- The involvement either directly or indirectly of a large number of people.

- The handling of a large number of enquiries likely to be generated both from the public and the news media, usually to the police.

- The need for the large scale combined resources of two or more of the emergency services.

- The mobilisation and organisation of the emergency services and supporting organisations eg. Local authority, to cater for the threat of death, serious injury or homelessness to a large number of people.

The event is attended by over 1000 participants plus spectators on the day and so the risk of emergency incidents is present. In order to enable any emergency to be dealt with efficiently and safely, the following procedures are in place;

BOMB WARNING RECEIVED
If a bomb warning is received by the police, media or organisers, the following procedures will take place;

- If a location is specified in the warning, the Event Safety Officer and police are consulted. Any unusual packages or behaviour reported to the police and the area may be closed to the public. If a package is located, the police will investigate and take the necessary action in evacuation with the help of the Event Safety Officer and stewards.

- If no location is specified, a site meeting will be called with the Event Safety Officer, and a Police Liaison. The site meeting will take place in the Event Control Unit located adjacent to the finish area.

The procedures to follow will be directed by the police and could include a detailed search of all event areas, evacuation of all areas or partial evacuation of a particular area, and further investigation into the validity of the warning.

COMPLETE EVACUATION OF THE EVENT AREAS
If a complete evacuation of the town centre is required, the police will assist. An emergency meeting of all stewards will be called, and the situation explained to them. Stewards will be responsible for moving all competitors, staff and spectators including event traders to the nearest egress route and clear the area. The event PA system will be used to give information to the public regarding the evacuation, the police will advise on the wording to be used. Once stewards have cleared the area, they will report to the Event Safety Officer who will ask them to stand by, evacuate or assist in another area. The Event Safety Officer will remain in constant communication with the police to ensure they are aware of the progress of the evacuation.

Participants will be stopped at the next available point on the course and will be prevented from re-entering the evacuated area until the situation has been fully assessed.

SUSPICIOUS PACKAGES
If a suspicious package is notified to a steward, they must contact the Event Safety Officer who will contact the police. The steward should be consulted as to any details they may have about the package and movements in the vicinity. The police will ascertain the seriousness of the package and may require partial evacuation, which will be conducted by the steward with the assistance of the police. The police will then proceed with the investigation.

FIRE
If a steward discovers a fire, they will raise the alarm by shouting. Evacuate all people that might be at risk. The steward will contact the emergency services by dialling 999 and then notify the Event Safety Officer or send someone to notify the Event Safety Officer. The Event Safety Officer will also notify the emergency services and then ensure that the police, event staff and Traffic Management Officer are aware and are expecting a fire engine. The police will ensure safe passage of the fire engine to the fire. The fire engine crew will deal with the fire as necessary.

Participants will be stopped at the next available point on the course and will be prevented from re-entering the evacuated area until the situation has been fully assessed.

HOSTILE AND NON-HOSTILE DEMONSTRATIONS
If a demonstration takes place at the event location, either by an individual or a group, the stewards should notify the Event Safety Officer immediately. The Event Safety Officer will notify the police and a site meeting held to decide on the best course of action. It may be necessary for a steward to ask the individual to cease their actions and leave the event area, if they do not leave, the police will assist.

CRIMINAL INCIDENT
If a criminal incident occurs, the steward should notify the Event Safety Officer who will notify the police. If there is a direct risk to life, then contact the police first then notify the Event Safety Officer or send someone to notify the Event Safety Officer. The police will deal with the situation in the appropriate manner and request a site meeting or evacuation.

ROAD INCIDENT
If an incident occurs on the roadways incorporating the event, the Event Safety Officer and police should be notified. The police will deal with the incident as quickly as possible and may re-route traffic as necessary. Stewards may be asked to help with re-routing or directing of the traffic.

EMERGENCY SITUATION
A pre-evacuation message will be notified to you from the Event Safety Officer. You should prepare for possible imminent evacuation.

The pre-evacuation message is: “All stewards operate a Code Black”.

If a full evacuation of your area is necessary, a public announcement will be made from the stage and/or PA system and/or you will be notified via radio or mobile phone from the Event Safety Officer.

The announcement will be: “Your attention please – for your own safety, please leave the event area by the exit directed by stewards”.

You must physically point and shout in the direction of safe exit during the evacuation. Your responsibility is to follow the instruction of the Event Safety Officer or emergency services in coordinating the evacuation. Once the evacuation is complete, and you are in a safe area, seal off the area and prevent re-admittance. Await further instructions.

## Lost Items/Property

Lost property will be difficult to locate due to the location and size of event. However, any item found at the start/finish areas will be taken to the Control Unit situated adjacent to the finish area. Items will be booked in and not released until the claimant can provide an adequate description of the item. Where ownership cannot be proven or is contested, the matter will be passed to the police. Any valuable item left unclaimed at the end of the event will be handed to the police. All other property will be disposed of.

## Lost Children

The lost children point will be located within the event registration/enquiry marquee and will be staffed by CRB/DBS checked personnel for the duration of the event. If a lost child is found, the steward who finds them or is handed them should remain at the point in which the child was found for several minutes and then contact the Event Safety Officer, who will advise if the child has been reported missing or whether he/she should be taken to the lost children point as detailed above.

Details of the child’s location when found, clothing, age and description are ascertained and if the child can communicate, details of parents are asked from him/her and reported to the Event Safety Officer who will pass the information onto the lost children point. The Event Safety Officer will notify the police of the details and ask the PA announcer to announce that a child has been found and asking parents/guardians to report to the lost children point. Details and colour of the child’s coat/clothing is the only information that can be given out in the announcement.

- DO NOT REFER TO CHILDREN SPECIFICALLY OR GIVE DETAILS OF NAME, SEX OR AGE

Stewards will direct all members of the public who have either lost someone or are looking for someone to the lost children point. If a parent arrives looking for a child who is not there, use radios to circulate a description of the child to stewards. Upon the parent/guardian arriving to collect the missing person, they must be asked for the child’s name, age, sex and a description of the child’s clothing and this should be checked against the available information. Details of the person claiming the missing person will be noted down and given to the Event Safety Officer to record it officially. If there is any doubt as to the validity of the parent/guardian claim on the missing person, the police should be called, and the matter dealt with by them. Missing persons not collected by the time the event closes, will be handed over to the police.

THE AIM OF THESE GUIDELINES IS TO PROTECT THE LOST CHILDREN AND EVENT STAFF FROM POSSIBLE LEGAL REPERCUSSIONS

# Communications

## Event Communications Profile

Communication between all those involved in the delivery of the event on the day will be a key factor in ensuring that a safe and successful event takes place. The means of communication will vary from the use of a bespoke network of radio communication, mobile phones and word of mouth between individuals.

Key staff will be based at the start/finish areas and at the event registration/enquiry marquee. They will primarily make use of the radio network brought in for the event period.

## Event Radio Network

The network will be provided and installed by RMS AMBULANCE on the day of the event. Radios must be collected and signed for from the Medical Tent located at the start/finish area of the event.

# Appendix A

## UK Athletics Event Adjudicator Form

Name of Race:	BLACKPOOL MUSIC RUN

Date of Race:

| No. | Area | Yes | No | N\A |
| --- | --- | --- | --- | --- |
| 1 | Race Information |  |  |  |
|  | Was the start area traffic free? |  |  |  |
|  | Was the finish area traffic free? |  |  |  |
|  | Were there marshals to assist runners in the following areas and did the level of cover provided match that detailed in the Event Plan and/or briefing documents? |  |  |  |
|  | Start Line |  |  |  |
|  | Pre-Finish |  |  |  |
|  | Finish |  |  |  |
|  | Post Finish |  |  |  |
|  | Were marshals briefed before the event? |  |  |  |
|  | Were marshals located in the correct positions as detailed in the Event Plan and/or briefing documents? |  |  |  |
|  | Were marshals wearing distinctive tabards/bibs/tops? |  |  |  |
| 2 | Signage |  |  |  |
|  | Was there signage in the following areas? |  |  |  |
|  | Start Line |  |  |  |
|  | Information |  |  |  |
|  | Changing |  |  |  |
|  | Toilets |  |  |  |
|  | Baggage |  |  |  |
|  | Finish |  |  |  |
|  | Further Comments on this Section |  |  |  |
| 3 | Course Review | Yes | No |  |
|  | Was the course signed? |  |  |  |
|  | Was there are Lead Vehicle or Cyclist?* |  |  |  |
|  | Was there a Sweep Vehicle/Cyclist or back marker?* |  |  |  |
|  | Was the course Traffic Free? |  |  |  |
|  | Were there mile or kilometre markings on the course? |  |  |  |
|  | Further Comments on this Section |  |  |  |
| 4 | Water Stations | Yes | No | N/A |
|  | Did the event provide water stations? If No skip forward to A |  |  |  |
|  | Were the water stations off the running line? |  |  |  |
|  | Were there advance signs for the water station/s? |  |  |  |
|  | Were adults operating or supervising the water station/s? |  |  |  |
|  | Were volunteers wearing distinctive tabards/bibs/tops? |  |  |  |
| A | Was water provided to all athletes at the end of the race? |  |  |  |
|  | Were the water stations of sufficient length for the size of the field? |  |  |  |
|  | Further Comments on this Section |  |  |  |
| 5 | Medical Provision | Yes | No |  |
|  | Was there Medical Provision at the event? |  |  |  |
|  | Who provided this Service? Details: |  |  |  |
|  | Was the Medical Risk Assessment available for inspection? |  |  |  |
|  | Was the medical information template printed on the back of the race number? |  |  |  |
|  | Further Comments on this Section |  |  |  |
| 6 | Risk Assessment | Yes | No |  |
|  | Was the Risk Assessment available for inspection? |  |  |  |
|  | Further Comments on this Section |  |  |  |
| 7 | Certification | Yes | No |  |
|  | Was there a need for a UKA Course Measurement Accuracy Certificate for the event? |  |  |  |
|  | If yes was it on display? |  |  |  |
|  | Race Promoter confirmed that measured course was run |  |  |  |
|  | Further Comments on this Section |  |  |  |
| 8 | Incidents |  |  |  |
|  | Please describe any incidents not covered by the previous questions: |  |  |  |
|  | Did you share any of your comments with the Race Promoter before submitting this report |  |  |  |
|  | Please explain why: |  |  |  |
|  | Further comments: |  |  |  |

When applying for a race licence, the Race Director agreed to meet runbritain Licence Standards. If you identify any areas where Licence Standards have not been achieved, please note this in the comments section.

This form is to be completed online within 7 days of the event and will be reviewed by the Regional Panel.

If you did not witness any of the above please identify who your source of information came from e.g. athletes or additional helper.

EVENT ADJUDICATOR:	Stephen Ashcroft

# Appendix B

## Tramway Activity Permit

Tramway Activity Permit Application

PART 1 Contact Details

Please Print Clearly in all fields

| Name of Person applying for safety permit The Duty Holder LEWIS MCANDREW |  |
| --- | --- |
| Address BLACKPOOL MUSIC RUN c/o FYLDE COAST RUNNERS UNIT 1A HOO HILL ESTATE |  |
| Town BLACKPOOL |  |
| County LANCASHIRE |  |
| Post Code FY3 7HJ |  |
| Tel No. 01253 394038 | E-mail ADMIN@FYLDECOASTRUNNING.ORG |

Brief activity details to be undertaken by The Duty Holder 10K RUNNING EVENT ON BLACKPOOL PROMENADE AND COMEDY CARPET AREA W/T

Address PROMENADE AT COLUMN 260 JUST SOUTH OF TOWER, BLACKPOOL

Exact Location

Column Numbers if applicable

Nature of Activity 10K RUNNING EVENT

Activity Date(s) SUNDAY 16th JUNE 2019

Permit Duration Requested 11.00AM – 2.00PM

| Permit Charges. All applications are subject to an administration fee of £125 plus VAT (charitable events are exempt). If an isolation of the overhead power supply is required an additional charge will be levied to ALL applications. You will be advised of the charges for isolation. Permit Application Fee payable Yes No (charities only) Isolation charges Yes No Please tick all necessary requirements |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Access Across Track |  | Isolation of Overhead |  | Closure Single Line |  |  |
| Closure Both Lines |  | Open Line Operation |  | Hold an Event |  |  |
| Access to Infrastructure |  | Other |  |  |  |  |
| If other please explain and give details. For events please indicate the number of organisers vehicles along with an estimated size of the audience. |  |  |  |  |  |  |
| SINGLE CROSSING OF TRAMWAY FOR ATHLETES AT COLUMN 260. CONTROLLED AREA WITH STEWARDS AND BTS CONDUCTOR. |  |  |  |  |  |  |

Emergency Contact Details

During normal hours

Name LEWIS MCANDREW

Tel No. 01253 394038

Outside normal hours

Name LEWIS MCANDREW

Tel No. 07488 275276

Signed								Date

…………………………………………………………		1 APRIL 2019

Duty Holder

PART 2 Competency Submission

Full explanation and description of activity

10K RUNNING EVENT ON BLACKPOOL PROMENADE AND COMEDY CARPET AREA W/T CROSSING POINT OF TRAMWAY.

| The following information MUST be included with the submission |  |  |
| --- | --- | --- |
| Plan showing layout of activities and transit routes |  |  |
| Risk Assessments |  |  |
| Method Statements |  |  |
| Safe Systems of Work |  |  |
| Details of Insurance |  |  |
| Relevant Training Records |  |  |

Permit No. PART 3 A copy of this Permit must be displayed/retained on site at all times

| Duty Holder Details |  |
| --- | --- |
| Full Name |  |
| Date of Application |  |
| Location |  |
| Permit Requirements |  |
| Start Date: | Time: |
| End Date: | Time: |

| Limitations of Permit |  |
| --- | --- |
| Signed on by: Blackpool Council …………………………………………………… | Agreed by: Blackpool Transport Services ……………………………………………………. |
| Dual signature required |  |
| Permit Charges Permit application fee £…………. + VAT Isolation fee £…………. +VAT Total charges £………….. +VAT | Copy forwarded to Blackpool Transport Date …………………………………………………… |